## Sheet1
Task Description | Start Date | End Date | Team Member | Status
Dadabase Design and insertstatements | 2019-06-03 | 2019-06-03 | Ishan dudeja | Done
Data Model and CRUD Function | 2019-06-04 | 2019-06-04 | Ishan dudeja | Done
Home Screen and android Side menu | 2019-06-05 | 2019-06-05 | Ishan dudeja | Done
Moudle List by pathway design and working | 2019-06-06 | 2019-06-06 | Ishan dudeja | Done
Module Dashboard layout design and working | 2019-06-07 | 2019-06-07 | Ishan dudeja | Done
Task Master (admin) navigatioin and design | 2019-06-08 | 2019-06-08 | Ishan dudeja | Done
Module Map Search and Card List working | 2019-06-09 | 2019-06-09 | Ishan dudeja | Done
Module Master Search and Card List working | 2019-06-10 | 2019-06-10 | Ishan dudeja | Done
Login activity desing | 2019-06-11 | 2019-06-11 | Ishan dudeja | Progress
About Screen design and working |  |  | Sourabh Sing
Declaration Screen working and design |  |  | Amandeep Kaur
Student Master (add Student) workiing and design |  |  | Ritika Kumar
Redesign of Home Screen Card Layout |  |  | Amandeep Kaur
Redesign side menu |  |  | Amandeep Kaur
Update presentation |  |  | Taehuri Tarawhiti
Create video + final Presentation |  |  | James Akash and Taehuri Tarawhiti
Redesign Layout for Student Card |  |  | Taehuri Tarawhiti
Redesign Layout for Module Card |  |  | Taehuri Tarawhiti
Student Edit working and design |  |  | Ritika Kumar
Assign map to Student working |  |  | Ishan Dudeja
Module edit Screen design and working |  |  | Sourabh Sing
Module Oberview Screen working and design |  |  | James Akash
Module Topic Screen design and working |  |  | James Akash
Assignments Screen design and working |  |  | Amandeep Kaur
Insert statement for Module |  |  | Ritika Kumar